## Tracker
DEFECT / BUG LOG
Defect ID | Date | Feature | Description | Severity | Priority | Reported By | Assigned To | Status | Fix / Resolution | Retest Result | Evidence
D-01 | 2026-10-22 | Bookings API and My bookings | Booking dates came back as time zone shifted dates because the raw slot_date was returned so a booking could show on the wrong day | High | High | Willem Gerber | Willem Gerber | Closed | DATE_FORMAT used for the date in the bookings queries (commit 87cefdb) | Pass: dates match the stored dates (TC-05 and TC-09) | routes/bookings.js and TC-05
D-02 | 2026-10-22 | Book a slot page | Time buttons show only "to" and the confirm panel shows "undefined to undefined" because the page reads start and end but the Slots API sends startTime and endTime | High | High | Willem Gerber | Willem Gerber | Fixed | Map startTime and endTime to start and end in loadSlots in BookSlot.jsx. Fix is in the working copy and not yet committed | Pass: 09:00 to 09:30 and 09:30 to 10:00 (TC-32) | TC-32 and times_before.png and times_after.png
D-03 | 2026-10-22 | Lecturer slots page | The merged page does not work with the Slots API: it calls /api/slots/my but the route is /api/slots/mine so the list shows That API route does not exist and it sends start and end but the API needs startTime and endTime so publishing fails (FR-03 and FR-09) | High | High | Willem Gerber | Thomas du Plessis | Fixed | Use /api/slots/mine and send startTime and endTime and map them when listing in LecturerSlots.jsx. Fix is in the working copy and not yet committed | Pass: the list shows the slots and publish and remove both work (TC-25 and TC-33) | TC-25 and TC-33 and D-03_fix_LecturerSlots.patch
D-04 | 2026-10-22 | My bookings page | No change button although the API supports changing a booking (FR-06) | Medium | Medium | Willem Gerber | Willem Gerber | Fixed | Added a Change time button on My bookings that lists the other open times of that lecturer and calls PATCH /api/bookings/:id/change. The bookings API now also returns lecturerId. Not yet committed | Pass: the booking moved and the notice showed (TC-29) | TC-29 and TC-06
D-05 | 2026-10-22 | Session handling | An expired or invalid token leaves the user on the page with an error and the old token is kept instead of going to the login page | Medium | Medium | Willem Gerber | Lebohang Tlaitlai | Fixed | Response interceptor in api.js clears the saved login and goes to /login with the message Your session has ended on a 401. Not yet committed | Pass (TC-28) | TC-28 and laptop_expired.png
D-06 | 2026-10-22 | Login security | There is no limit on repeated wrong passwords so 40 attempts in a row were all answered | Medium | Medium | Willem Gerber | Willem Gerber | Fixed | Login allows 10 wrong passwords per account and address in 15 minutes and then answers 429. Not yet committed | Pass: attempts 11 and 12 gave 429 and another account still logged in (TC-30) | TC-30
D-07 | 2026-10-22 | Documentation | Chapter 4 says the reminder scheduler runs every 15 minutes but the code runs it every minute | Low | Low | Willem Gerber | Willem Gerber | Fixed | Chapter 4 text changed to every minute. The architecture diagram label should be checked in the final dissertation | Pass: the text matches jobs/reminders.js | Chapter 4 section 4.2 and jobs/reminders.js
D-08 | 2026-10-22 | Book a slot page | After a failed booking the reason box is hidden until a time is chosen again although the typed text is kept | Low | Low | Willem Gerber | Willem Gerber | Fixed | The confirm step stays visible after an error unless the slot was taken. Not yet committed | Pass (TC-16b) | TC-16b
D-10 | 2026-10-22 | Lecturer slots page | The page can publish and remove slots but has no way to edit a slot although the API supports editing (FR-03) | Medium | Medium | Willem Gerber | Thomas du Plessis | Fixed | Added an Edit button that fills the form and saves with PUT /api/slots/:id. Not yet committed | Pass: the new location was saved (TC-34) | TC-34
D-09 | 2026-10-22 | Route protection | A logged in user who opens the other roles page is sent to the login page and not to their own home page | Low | Low | Willem Gerber | Lebohang Tlaitlai | Fixed | ProtectedRoute sends the user to their own home page. Not yet committed | Pass (TC-27) | TC-27