## Tracker
SOFTWARE TEST CASES & RESULTS
Test ID | Requirement ID | Feature | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Date | Evidence
TC-01 | FR-01 | Login | Database seeded with the test users | 1 Send valid student login 2 Send valid lecturer login 3 Send a wrong password 4 Send an unknown email | Password CampusBook123 for all test users | Valid logins return a token and role. Wrong password and unknown email give the same general error | student 200 role student; lecturer 200 role lecturer; wrong password 401 "Email or password is incorrect"; unknown email 401 "Email or password is incorrect" | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-02 | FR-02 | Role checks on the server | Student and lecturer tokens available | 1 Student posts a slot 2 Lecturer posts a booking 3 Call a route with no token 4 Student calls lecturer routes | Requests sent straight to the API | Wrong role gets 403 and no token gets 401 | student creates slot 403; lecturer books 403; no token 401; student reads lecturer bookings 403; student reads lecturer slots 403 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-03 | FR-03 | Lecturer manages own slots | Two lecturers logged in | 1 Lecturer 1 publishes a slot 2 Edits it 3 Lecturer 2 tries to edit and delete it 4 Lecturer 1 deletes it | Future date with start 08:00 and end 08:30 | Owner can publish edit and remove. Another lecturer gets 404 | create 201; edit 200 end 08:45 location Teams; other lecturer edit 404; other lecturer delete 404; owner delete 200; slot still listed after delete: false | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-04 | FR-04 | Student views open slots | One past slot and several future slots stored | 1 Student requests slots for lecturer 1 | lecturerId=1 with one past slot added | Only future slots with status open are listed | 200 3 slots listed of 4 stored for the lecturer; all open: true; all lecturer 1: true; past slot listed: false | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-05 | FR-05 | Book a slot | An open future slot | 1 Student posts a booking with a reason 2 Read the booking and slot from the database | Reason: Help with my ERD | Booking saved with student slot and reason and the slot becomes booked | 201; saved student 3 slot 1 reason "Help with my ERD" status confirmed; slot status booked; response has date 2026-10-23 09:00 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-06 | FR-06 | Change and cancel a booking | A confirmed booking and a second open slot | 1 Change the booking to another slot 2 Cancel the new booking 3 Cancel it again | Same student token | Old slot opens after a change and after a cancel. Second cancel is refused | change 200 (old slot open new slot booked); cancel 200 (slot open booking cancelled); second cancel 404 "Upcoming booking not found" | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-07 | FR-07 | No double booking | One open slot and three student accounts | 1 Send 8 booking requests for the same slot at the same moment | 8 parallel requests from 3 students | Exactly one confirmed booking and the rest get the slot taken message | 8 simultaneous requests gave 1 created and 7 rejected with 409 "Sorry that slot is no longer available"; confirmed bookings in database 1 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-08a | FR-08 | Confirmation email | Email service in preview mode (no SMTP host set) | 1 Book a slot 2 Read the server email preview and the notifications table | Student and lecturer test emails | Confirmation to the student and a notice to the lecturer and the confirmation is marked sent | preview log shows student and lecturer emails with subject Consultation booked: true; notification rows for the booking: confirmation:sent | Pass | 2026-10-22 | test_scripts/api_tests.js and server log
TC-08b | FR-08 | Reminder email | A booking with a pending reminder | 1 Move the reminder time into the past 2 Run the reminder job | Reminder job processDueReminders | Reminder sent to student and lecturer and marked sent | reminder row before: pending; after running the reminder job: sent; reminder text mentions student and lecturer: true | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-09 | FR-09 | Booking history | Bookings from several students | 1 Read my bookings for two students 2 Read lecturer bookings for both lecturers | Cancelled and confirmed bookings | Each user sees only their own records and cancelled bookings stay in the history | student 1 sees 3 bookings student 2 sees 0; no shared ids: true; lecturer 2 sees 1 booking(s) and lecturer 1 sees 2 (race slot belongs to lecturer 2: shown to lecturer 1 = false); history includes cancelled: true | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-10 | NFR-01 | First time student books in under 2 minutes | Phone sized screen | 1 Run the login to booking journey as a script and time it | 375 pixel wide browser | Under 120 seconds with real students | Scripted run on a phone screen took 1.9 seconds from login to the confirmation. The timed task with real students is planned for Week 5 user testing | Not Run | 2026-10-22 | test_scripts/ui_tests.js and Week 5 user testing
TC-11 | NFR-02 | Main pages load in under 3 seconds | Production build served by vite preview | 1 Time the login page 2 Time the book page after login 3 Time my bookings | Chromium at 375 and 1366 pixels | Each page loads in under 3000 ms | phone: login 127 ms book after login 305 ms my bookings 382 ms; laptop: login 82 ms book after login 218 ms my bookings 387 ms | Pass | 2026-10-22 | test_scripts/ui_tests.js
TC-12 | NFR-03 | Phone and laptop layout | Production build running | 1 Open each page at 375 and 1366 pixels 2 Compare page width with window width | Login book my bookings lecturer slots | No sideways scrolling on any page | phone login: no sideways scroll; phone book: no sideways scroll; phone book with calendar: no sideways scroll; phone my bookings: no sideways scroll; phone lecturer slots (/lecturer/slots): no sideways scroll; laptop login: no sideways scroll; laptop book: no sideways scroll; laptop book with calendar: no sideways scroll; laptop my bookings: no sideways scroll; laptop lecturer slots (/lecturer/slots): no sideways scroll | Pass | 2026-10-22 | test_scripts/ui_tests.js and evidence screenshots
TC-13 | NFR-04 | Passwords stored as bcrypt hashes | Seeded database | 1 Read every password_hash 2 Check the login code | All 7 users | Only 60 character bcrypt hashes and login uses bcrypt compare | 7 users checked: all bcrypt format true; none equal to the plain password true; auth.js uses bcrypt.compare: true | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-14 | NFR-05 | Users cannot reach other records | A booking owned by one student | 1 Another student cancels it 2 Another student changes it 3 Another lecturer edits the slot | Tokens of other users | All refused with 404 and nothing changes | other student cancel 404; other student change 404; other lecturer edit 404; booking still confirmed | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-15 | NFR-06 | Only needed data is stored | Seeded database | 1 List every table and column 2 Check the test users | information_schema | No sensitive columns and every user is on the test email domain | tables: bookings(booking_idslot_idstudent_idreasonstatuscreated_atupdated_atactive_slot_id); consultation_slots(slot_idlecturer_idslot_datestart_timeend_timelocationstatuscreated_at); lecturer_profiles(lecturer_iddepartmentoffice); notifications(notification_idbooking_idtypesend_atsent_atstatus); users(user_idfull_nameemailpassword_hashrolestudent_numbercreated_at); users not on the test domain: 0; sensitive column names found: false | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-16 | NFR-07 | Errors explain what to fix (API) | Server running | 1 Send empty login 2 Send a long and a blank reason 3 Send no slot | Invalid bodies | 400 with a plain message and nothing saved | SQL style login 400 "Enter a valid email address" and 400; empty login Enter a valid email address Enter your password; reason too long 400 "Give a short reason for the visit (up to 255 characters)"; blank reason 400 "Give a short reason for the visit (up to 255 characters)"; no slot 400 "Choose a slot" | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-16b | NFR-07 | Errors on screen and kept input | Production build running | 1 Log in with a wrong password 2 Submit an empty form 3 Book a slot that another student takes first | Typed reason My typed reason should stay | Plain messages and the typed text is kept | Before the fixes: after a failed booking the reason box was hidden and the confirm step had to be started again (D-08). After the fixes: wrong password message "Wrong email or password please try again" and email kept "willem.gerber@campusbook.test"; empty form message "Enter your email address and your password."; slot taken message "Sorry that slot is no longer available" ; the reason box was hidden after the error: true; after choosing another time the reason box still holds "My typed reason should stay" | Pass | 2026-10-22 | test_scripts/ui_tests.js
TC-17 | FR-05 | Book a missing past or taken slot | Slots in different states | 1 Book slot 999999 2 Book a past slot 3 Book a booked slot | Three bad slot ids | 409 with Sorry that slot is no longer available | missing slot 409 "Sorry that slot is no longer available"; past slot 409; booked slot 409 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-18 | FR-03 | Slot validation rules | Lecturer logged in | 1 Publish slots with bad times dates and an overlap | End before start and past date and 31 February and empty location and overlap | Refused with a message that says what to fix | end before start: 400 "The end time must be after the start time"; past date: 400 "Choose a time in the future"; 31 February: 400 "Enter a valid date (YYYY-MM-DD)"; invalid time: 400 "Enter a valid start time (HH:MM) Enter a valid end time (HH:MM)"; empty location: 400 "Enter a location (up to 100 characters)"; overlap: 409 "This overlaps another one of your slots" | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-19 | FR-03 | Booked slot cannot be edited or removed | A slot booked by a student | 1 Lecturer edits it 2 Lecturer deletes it | Booked slot | 409 for both | booking 201; edit 409 "A booked slot cannot be changed or removed. Ask the student to cancel first"; delete 409 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-20 | FR-03 | Removing a slot keeps history | A slot with a cancelled booking | 1 Lecturer removes the slot 2 Publish the same time again | Same date and start time | Slot marked cancelled and history kept and publishing again reopens it | delete 200; slot status cancelled; bookings kept 1; republish 201 same id true status open | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-21 | FR-02 | Bad ids bad JSON and unknown routes | Server running | 1 Send letters as ids 2 Send broken JSON 3 Call an unknown route | abc and {bad json | 400 or 404 with a clear message and no server error | bad booking id 400 "Invalid booking"; bad lecturer id 400 "Choose a lecturer"; bad slot id 400; invalid JSON 400 "The request body is not valid JSON"; unknown route 404 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-22 | FR-01 | Forged expired and garbage tokens | Server running | 1 Call a route with each bad token | Wrong secret and expired and garbage | All refused with 401 | forged 401; expired 401 "Your session has expired please log in again"; garbage 401 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-23 | NFR-02 | Health check | Server running | 1 Call GET /api/health | None | 200 and ok true | 200 {"ok":true} | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-24 | NFR-02 | API response time for the slot list | Server running | 1 Send 20 requests for the slot list and time them | lecturerId=1 | Under 500 ms for every request | 20 requests: median 6 ms slowest 21 ms | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-25 | FR-03 and FR-09 | Lecturer publishes a slot from the page | Lecturer account and the Lecturer slots page | 1 Log in as a lecturer 2 Read the slot list on /lecturer/slots 3 Fill the form and press Publish slot | jabulile.mashibini@campusbook.test and a slot 5 days ahead from 14:00 to 14:30 | The page lists the lecturer slots and publishing saves the slot | Before the fixes (commit e9ab578): the list failed with "That API route does not exist" because the page called GET /api/slots/my and the route is /api/slots/mine and publishing showed "Enter a valid start time (HH:MM) Enter a valid end time (HH:MM)" because the page sent start and end and the API needs startTime and endTime and nothing was saved. After the fixes: the list shows the slots and publishing returns 201 and the slot is saved | Pass | 2026-10-22 | test_scripts/lect_tests.js and evidence lecturer_before_laptop.png and lecturer_after_laptop.png
TC-26 | FR-08 | Reminder not sent for a cancelled booking | A booking with a reminder due | 1 Book 2 Make the reminder due 3 Cancel 4 Run the job | Reminder rows | No reminder left to send | reminder rows left for the cancelled booking: 0 | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-27 | FR-02 | Pages protected by login and role | Production build running | 1 Open /book with no login 2 Student opens the lecturer page 3 Lecturer opens /book | Browser navigation | Visitors go to login and each role is sent to their own home page | Before the fixes: a student or lecturer opening the other roles page was sent to the login page (D-09). After the fixes: not logged in opening /book goes to /login; student opening /lecturer/slots goes to /book; lecturer opening /book goes to /lecturer/slots | Pass | 2026-10-22 | test_scripts/ui_tests.js
TC-28 | NFR-07 | Expired or invalid session | Student logged in | 1 Replace the saved token with an invalid one 2 Open my bookings | Invalid token | User is sent to the login page with a clear message | Before the fixes: the user stayed on the page with an error and the old token was kept (D-05). After the fixes: after the token became invalid the page stayed at /login and showed "Your session has ended. Please log in again." | Pass | 2026-10-22 | test_scripts/ui_tests.js and laptop_expired.png
TC-29 | FR-06 | Change a booking from the page | A confirmed booking | 1 Open my bookings 2 Look for a change button 3 Change the booking to another time | willem.gerber@campusbook.test | A change button is offered next to cancel and moving the booking works | Before the fixes: only a Cancel booking button was offered (D-04). After the fixes: buttons on the booking rows: ["Change time""Cancel booking"] and moving the booking showed the notice Your booking has moved and the lecturer has been told | Pass | 2026-10-22 | test_scripts/extras_tests.js and ui_tests.js
TC-30 | Security (extra) | Repeated wrong passwords are limited | Server running | 1 Send wrong passwords for one account 2 Then send the correct password for another account | willem.gerber@campusbook.test | The attempts are blocked after several failures and other accounts are not affected | Before the fixes: all 40 wrong passwords were answered with 401 and no limit applied. After the fixes: the first 10 wrong passwords gave 401 and the next 2 gave 429 Too many failed attempts and another account still logged in with 200 | Pass | 2026-10-22 | test_scripts/extras_tests.js (D-06)
TC-31 | FR-07 | Database refuses a second confirmed booking | A confirmed booking exists | 1 Insert a second confirmed booking straight into the database | Same slot id | Insert fails with a duplicate key error | direct insert gave ER_DUP_ENTRY | Pass | 2026-10-22 | test_scripts/api_tests.js
TC-32 | FR-04 | Times shown on the Book a slot page | Main branch at commit e9ab578 | 1 Log in as a student 2 Choose a lecturer 3 Read the time buttons 4 Pick a time and read the confirm panel | Lecturer 1 with two slots tomorrow | Each time button shows the start and end like 09:00 to 09:30 | Before the fix: buttons showed only "to" and the confirm panel showed "undefined to undefined". After the fix: buttons show 09:00 to 09:30 and 09:30 to 10:00 | Pass | 2026-10-22 | times_before.png and times_after.png
TC-33 | FR-03 | Lecturer removes a slot from the page | Lecturer account and the Lecturer slots page | 1 Open /lecturer/slots 2 Press Remove on a slot and confirm | An open slot of lecturer 1 | The slot is removed and the list updates | Before the fixes: blocked because the list never loaded so there was no slot to remove. After the fixes: the notice Consultation slot removed shows and the row leaves the list (DELETE returned 200) | Pass | 2026-10-22 | test_scripts/lect_tests.js
TC-34 | FR-03 | Lecturer edits a slot from the page | Lecturer account and the Lecturer slots page | 1 Open /lecturer/slots 2 Press Edit on a slot 3 Change the location and press Save changes | Location changed to Room C3 | The page offers an edit option and the change is saved | Before the fixes: the page only had a Remove button and no edit option although the API supports editing with PUT /api/slots/:id (D-10). After the fixes: Edit fills the form and Save changes shows Consultation slot updated and the database holds the new location (PUT returned 200) | Pass | 2026-10-22 | test_scripts/lect_tests.js and lecturer_edit_laptop.png