## Tracker
PROJECT RISK, ISSUE & CHANGE REGISTER
ID | Type | Date | Description | Likelihood | Impact | Priority | Owner | Mitigation / Action | Status | Due Date | Outcome
R-01 | Risk | 2026-10-19 | Not enough time to build all six features | High | High | High | Willem Gerber | Build the must-haves first and check commits daily | Open | 2026-10-29 | Eight of eight coding tasks merged on 22 October and testing fixes are retested
R-02 | Risk | 2026-10-19 | Work falls on one or two members | Medium | High | High | Willem Gerber | Clear owners for every task tracked on GitHub | Open | 2026-10-29
R-03 | Risk | 2026-10-19 | Some members are new to React or Express | Medium | Medium | Medium | Oscar Khumalo and Thomas du Plessis | Pair programming and the shared project structure | Open | 2026-10-29
R-04 | Risk | 2026-10-19 | Too few survey or test participants | Medium | Medium | Medium | Lebohang Tlaitlai | Share the survey early in class and on Teams | In Progress | 2026-10-29 | 13 students answered the survey on 22 October so the target of 10 was met and user testing numbers are still to be confirmed
R-05 | Risk | 2026-10-19 | Email reminders not working in time | Medium | High | High | Gerhardus van den Berg | Set up the email service early and test it | In Progress | 2026-10-29 | Email service built and merged in Week 4 and reminders still to be tested
R-06 | Risk | 2026-10-19 | Double booking or one user seeing another user data | Medium | High | High | Oscar Khumalo | Database unique key role checks and access tests | In Progress | 2026-10-29 | Unique key and role checks merged and access tests still to run
I-01 | Issue | 2026-10-16 | Survey target was 10 students |  |  | Medium | Willem Gerber | Both now say at least 10 students | Resolved | 2026-10-19 | Both documents now say at least 10 students
I-02 | Issue | 2026-10-16 | Supervisor approval for the survey and user testing |  |  | Medium | Willem Gerber | Confirm with Jabulile Mashibini before sending the survey | Open | 2026-10-23
I-03 | Issue | 2026-10-16 | First commits from every member |  |  | Medium | All members | Each member pushes their first commit before Monday 19 October 12pm | Resolved | 2026-10-19 | First commits pushed by 22 October
C-01 | Change | 2026-10-19 | Lecturer interviews replaced by lecturer feedback on the proposal (No formal interviews were held) |  |  | Low | Willem Gerber | Done in Week 2 | Resolved | 2026-10-19
C-02 | Change | 2026-10-19 | Survey target set to at least 10 students everywhere (Two different numbers were used) |  |  | Low | Willem Gerber | Done in Week 3 | Resolved | 2026-10-19
C-03 | Change | 2026-10-19 | App screenshots replaced by wireframes (The app is built in Week 4) |  |  | Low | Willem Gerber | Done in Week 3 | Resolved | 2026-10-19
C-04 | Change | 2026-10-19 | Test set up for the page load target written down (Makes NFR-02 repeatable) |  |  | Low | Willem Gerber | Planned for Week 4 | Open | 2026-10-23