## Tracker
PROJECT SCHEDULE & SPRINT BACKLOG
Task ID | Chapter/Sprint | Task / User Story | Owner | Start Date | Due Date | Priority | Status | % Complete | Evidence / Deliverable
T01 | Sprint 0 | Chapter 1 Introduction | Willem Gerber | 2026-10-16 | 2026-10-19 | High | Complete | 100% | Chapter 1 in the Week 3 PDF
T02 | Sprint 0 | Chapter 2 Literature review and matrix | Willem Gerber | 2026-10-16 | 2026-10-19 | High | Complete | 100% | Chapter 2 and Appendix C
T03 | Sprint 0 | Chapter 3 Requirements and methodology | Willem Gerber | 2026-10-16 | 2026-10-19 | High | Complete | 100% | Chapter 3 and SRS in Appendix D
T04 | Sprint 0 | Chapter 4 UML architecture and wireframes | Willem Gerber | 2026-10-16 | 2026-10-19 | High | Complete | 100% | Diagrams and wireframes in Chapter 4
T05 | Sprint 0 | Database design and SQL scripts | Willem Gerber | 2026-10-16 | 2026-10-19 | High | Complete | 100% | database/schema.sql and seed.sql
T06 | Sprint 0 | Project charter ethics form and work plan | Willem Gerber | 2026-10-16 | 2026-10-19 | Medium | Complete | 100% | Appendix A and Appendix E
T07 | Sprint 0 | GitHub repository set up and first commits | All members | 2026-10-15 | 2026-10-19 | High | Complete | 100% | Repository and commit history
T08 | Sprint 1 | Back-end set up and login | Willem Gerber | 2026-10-20 | 2026-10-20 | High | Complete | 100% | Pull request #1
T09 | Sprint 1 | Slots API | Lebohang Tlaitlai | 2026-10-21 | 2026-10-22 | High | Complete | 100% | Pull request #4
T10 | Sprint 1 | Bookings API | Willem Gerber | 2026-10-21 | 2026-10-21 | High | Complete | 100% | routes/bookings.js
T11 | Sprint 1 | Database and emails | Oscar Khumalo | 2026-10-21 | 2026-10-21 | High | Complete | 100% | Pull request #3
T12 | Sprint 1 | Front-end set up and Login page | Lebohang Tlaitlai | 2026-10-21 | 2026-10-21 | High | Complete | 100% | Pull request #2
T13 | Sprint 1 | Book a slot page | Willem Gerber | 2026-10-21 | 2026-10-21 | High | Complete | 100% | pages/BookSlot.jsx
T14 | Sprint 1 | Lecturer slots page | Thomas du Plessis | 2026-10-21 | 2026-10-22 | High | Complete | 100% | Commit c2ecca1 and pull request #6
T15 | Sprint 1 | My bookings page and phone layout | Willem Gerber | 2026-10-22 | 2026-10-22 | High | Complete | 100% | Commit 87cefdb
T16 | Sprint 1 | Student survey | Gerhardus van den Berg | 2026-10-20 | 2026-10-22 | Medium | Complete | 100% | 13 student answers in folder 06 (Group-3_Survey_Responses.xlsx) and Chapter 5 section 5.7
T17 | Sprint 1 | Testing workbooks and test cases | Willem Gerber | 2026-10-22 | 2026-10-23 | High | Complete | 100% | Folder 06 workbooks and Test Plan (defects fixed and retested)
T18 | Sprint 1 | Chapter 5 and Chapter 4 sections 4.6 to 4.8 | All members | 2026-10-22 | 2026-10-23 | High | Complete | 100% | Chapter 5 and Chapter 4 sections 4.6 to 4.9 done
T19 | Sprint 1 | Demo script and demo video | All members | 2026-10-22 | 2026-10-23 | Medium | Complete | 100% | Video recorded and linked on page 1 and the Demo Script and slides are in folder 11
T20 | Sprint 2 | Back-end fixes and security check | Willem Gerber | 2026-10-24 | 2026-10-26 | High | Complete | 100% | Fixed routes and access tests
T21 | Sprint 2 | Front-end fixes and polish | Lebohang Tlaitlai | 2026-10-24 | 2026-10-26 | Medium | Complete | 100% | Fixed pages
T22 | Sprint 2 | User testing with 5 students and 1 lecturer | Testing team | 2026-10-24 | 2026-10-26 | High | Not Started | 0% | Test evidence
T23 | Sprint 2 | Final Chapter 5 and Chapter 6 | All members | 2026-10-24 | 2026-10-26 | High | Not Started | 0% | Final chapters
T24 | Sprint 2 | Demo data demo laptop and backup video | All members | 2026-10-26 | 2026-10-27 | Medium | Not Started | 0% | Demo ready
T25 | Sprint 2 | Final slides and practice runs | All members | 2026-10-26 | 2026-10-28 | Medium | Not Started | 0% | Slides
T26 | Sprint 2 | Final dissertation and submission | Willem Gerber | 2026-10-28 | 2026-10-29 | High | Not Started | 0% | Final submission and live demo 29 Oct