CAPSTONE PROJECT
WEEKLY PROJECT PROGRESS REPORT

| Project Title | CampusBook: a lecturer consultation booking system for CTU Training Solutions |
| --- | --- |
| Group Members | Willem Gerber (Group Lead) Oscar Khumalo Thomas du Plessis Lebohang Tlaitlai Gerhardus van den Berg |
| Module | Software Engineering 2 (SPM622) |
| Lecturer / Supervisor | Jabulile Mashibini |
| Week / Stage | Week 4 |
| Submission Date | Friday 23 October 2026 |

# Week / Date

Week 4 Sprint 1 from Tuesday 20 to Friday 23 October 2026
Status as at Saturday 24 October 2026

# Planned Work

Back-end set up with login and role checks

Database connection plus the confirmation and reminder emails

Slots API and Bookings API with no double booking

React app with the Login page Book a slot page Lecturer slots page and My bookings page that all work on a phone

Student survey testing workbooks and the Chapter 4 and Chapter 5 sections

Demo Script and a 3 to 5 minute video for the Friday 23 October 12pm submission

# Completed Work

| Work | Who | Evidence on GitHub |
| --- | --- | --- |
| Back-end set up login and role checks | Willem Gerber | Commit 6f458c7 on 20 Oct (server.js routes/auth.js middleware) |
| React app routes and Login page | Lebohang Tlaitlai | Commit fe19ea8 and pull request #2 on 21 Oct |
| Bookings API and Book a slot page | Willem Gerber | Commits 6f458c7 and 590e891 on 20 and 21 Oct (routes/bookings.js pages/BookSlot.jsx) |
| Database connection and email reminders | Oscar Khumalo | Commit 5682abf and pull request #3 on 21 Oct (db.js mailer.js reminders.js) |
| Slots API | Lebohang Tlaitlai | Commit e9b5f3e and pull request #4 on 22 Oct (routes/slots.js) |
| My bookings page and phone layout | Willem Gerber | Commit 87cefdb on 22 Oct (pages/MyBookings.jsx) |
| Lecturer slots page | Thomas du Plessis | Commit c2ecca1 and pull request #6 on 22 Oct (pages/LecturerSlots.jsx) |
| Test Plan and test cases and Defect Log and Chapter 5 | Willem Gerber | Group-3 files in folder 06 and test_scripts and evidence |
| Task sign-up sheet for Week 4 and Week 5 | Willem Gerber | Group-3_Pick_Your_Tasks.docx shared with the group |

All 8 coding tasks are merged into main and the Test Plan and test cases and Defect Log and Traceability Matrix and Chapter 5 are written (folder 06) The student survey got 13 answers and is in Chapter 5 and Tom wrote Chapter 4.6 and 4.7 with 18 screenshots and it is now in the CTU layout

# Individual Contributions

| Member | This week |
| --- | --- |
| Willem Gerber | GitHub branches and reviews the shared page template back-end set up and login Bookings API Book a slot page My bookings page and phone layout task sheet testing and the Chapter 5 |
| Oscar Khumalo | Database connection confirmation and reminder emails (pull request #3) and his contribution form and Group Declaration signed |
| Thomas du Plessis | Lecturer slots page (commit c2ecca1 and pull request #6) Chapter 4.6 and 4.7 with screenshots then the slide outline and Demo Script |
| Lebohang Tlaitlai | React set up and Login page Slots API (pull requests #2 and #4) and the student survey |
| Gerhardus van den Berg | No Week 4 task picked yet |

# Challenges / Issues

The Lecturer slots page was merged after the code deadline on Thursday 22 October (commit c2ecca1 and pull request #6) and testing then found it did not work with the Slots API

Testing logged 10 defects and all 10 are fixed and retested (35 of 36 tests pass and 1 needs real students) The fixes and the new navy and cyan design were added after testing

Supervisor approval for the survey and user testing still needs to be confirmed

Dates from MySQL shifted by the time zone and this was fixed in routes/bookings.js

Members need MySQL installed on their own laptops to run the app

# Next Week Plan

| Action | Owner | Due |
| --- | --- | --- |
| Back-end fixes and security check | Willem Gerber | Mon 26 Oct |
| Front-end fixes and polish | Willem Gerber | Mon 26 Oct |
| User testing with 5 students and 1 lecturer | Not picked yet | Mon 26 Oct |
| Final Chapter 5 | Oscar Khumalo | Mon 26 Oct |
| Chapter 6 Conclusion and Recommendations | Lebohang Tlaitlai | Mon 26 Oct |
| Demo data and demo laptop | Willem Gerber | Tue 27 Oct |
| Final slides and backup demo video | Thomas du Plessis | Tue 27 Oct |
| Final dissertation and submission | Willem Gerber | Wed 28 Oct |
| Practice runs and the live presentation | All | 27 to 29 Oct |

# Supervisor Feedback

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Sign-off

Group Representative: Willem Gerber        Supervisor: ____________________        Date: __________