CAPSTONE PROJECT
PROJECT CHARTER & WORK PLAN

| Project Title | CampusBook: a lecturer consultation booking system for CTU Training Solutions |
| --- | --- |
| Group Members | Willem Gerber Oscar Khumalo Thomas du Plessis Lebohang Tlaitlai Gerhardus van den Berg |
| Module | Software Engineering 2 (SPM622) |
| Lecturer / Supervisor | Jabulile Mashibini |
| Week / Stage | Week 5 Final submission |
| Submission Date | Thursday 29 October 2026 |

# Project Overview

CampusBook is a web based consultation booking system for CTU Training Solutions Students currently arrange consultations through email Teams WhatsApp and walk-ins which leads to missed and unplanned meetings The project will build and evaluate a system that gives students and lecturers one place to manage consultations

| Project | CampusBook |
| --- | --- |
| Client | CTU Training Solutions students and lecturers |
| Supervisor | Jabulile Mashibini |
| Group Lead | Willem Gerber |
| Method | Scrum with one-week sprints |
| Duration | 16 October to 29 October 2026 |

# Aim and Objectives

The aim is to design develop and evaluate CampusBook so that fewer consultations at CTU are missed or left unplanned the five objectives are to analyse current practice compare existing systems build the six must have features test the system and evaluate it with real users

Objectives

1.	Analyse how consultations are arranged today through a survey of at least 10 students by 21 October 2026

2.	Compare at least three existing scheduling systems on their features strengths and limitations by 19 October 2026

3.	Design and develop a web system with all six must-have features working on a live database by 23 October 2026

4.	Test the system so that every must-have test case passes a booking takes under 2 minutes and pages load within 3 seconds

5.	Evaluate the system with at least 5 students and 1 lecturer with 80% or more rating it easy to use

# Scope and Deliverables

The project covers one CTU campus student and lecturer roles and the six must have features It excludes SMS video calls native apps and links to CTU live systems The deliverables are:

A working web application with source code on GitHub

A dissertation covering Chapters 1 to 6 with testing evidence

A live demonstration and presentation on 29 October 2026

# Team and Roles

| Member | Role | Responsible for |
| --- | --- | --- |
| Willem Gerber | Group Lead and Scrum Master | Stand ups GitHub board booking logic compiling the dissertation |
| Oscar Khumalo | Back-end developer | Express API login and roles back-end write-up |
| Thomas du Plessis | Front-end developer | React pages mobile layout and wireframes |
| Lebohang Tlaitlai | Testing and research lead | Student survey literature review test cases |
| Gerhardus van den Berg | Database developer | MySQL schema and ERD email reminders |

# Milestones

| Sprint | Main tasks | Milestone |
| --- | --- | --- |
| Sprint 0 16 to 19 Oct | Chapters 1 to 3 requirements system design charter ethics form GitHub set-up and first commits | Week 2 and 3 PDFs due Monday 19 Oct 12pm |
| Sprint 1 20 to 23 Oct | Database login slots and booking reminders history mobile layout student survey testing | Working app and Chapters 4 and 5 due Friday 23 Oct 12pm |
| Sprint 2 24 to 29 Oct | User testing bug fixes full dissertation check presentation practice | Final submission and live demo Thursday 29 Oct |

# Risks and Assumptions

| Risk | Level | How we handle it |
| --- | --- | --- |
| Not enough time to build every feature | High | Build the must-haves first and commit daily |
| Work falls on one or two people | High | Clear task owners checked at every stand up and on GitHub |
| Some members are new to React or Express | Medium | Pair programming and a shared starter project |
| Too few survey or test participants | Medium | Share the survey early in class and on Teams |

# Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Willem Gerber | Group Lead |  | 2026/10/22 |
| Jabulile Mashibini | Project supervisor |  |  |