## Tracker
REQUIREMENTS TRACEABILITY MATRIX
Requirement ID | Requirement Description | Type | Priority | Design / Component | Implementation Evidence | Test Case ID | Test Result | Final Status
FR-01 | Students and lecturers log in with their email and password | Functional | Must | routes/auth.js and Login.jsx | Login works for both roles and bad details give one general error | TC-01 and TC-22 | Pass | Met
FR-02 | The system checks the user role so students and lecturers only reach their own pages and actions | Functional | Must | middleware/auth.js and ProtectedRoute.jsx | Role checks on every route and page | TC-02 and TC-21 and TC-27 | Pass | Met
FR-03 | Lecturers publish edit and remove their own future consultation slots | Functional | Must | routes/slots.js and LecturerSlots.jsx | API works and is validated but the lecturer page is not built (D-03) | TC-03 and TC-18 and TC-19 and TC-20 and TC-25 | Fail | Partially Met
FR-04 | Students view the open slots of a chosen lecturer | Functional | Must | routes/slots.js and BookSlot.jsx | Slots listed correctly but the page does not show the times until D-02 is merged | TC-04 and TC-32 | Fail | Partially Met
FR-05 | Students book an open slot and give a short reason for the visit | Functional | Must | routes/bookings.js and BookSlot.jsx | Booking saved and confirmation shown | TC-05 and TC-17 | Pass | Met
FR-06 | Students change or cancel their own upcoming bookings | Functional | Must | routes/bookings.js and MyBookings.jsx | Cancel works in the page and change works in the API but there is no change button (D-04) | TC-06 and TC-29 | Fail | Partially Met
FR-07 | The system stops two students booking the same slot | Functional | Must | bookings.js transaction and unique active_slot_id | 8 simultaneous requests gave one booking | TC-07 and TC-31 | Pass | Met
FR-08 | The system sends an email confirmation after booking and a reminder before the meeting | Functional | Must | services/mailer.js and jobs/reminders.js | Confirmation and reminder work in preview mode. Real SMTP delivery is still to be tested on the demo laptop | TC-08a and TC-08b and TC-26 | Pass | Met
FR-09 | Students see their own booking history and lecturers see the bookings for their slots | Functional | Must | routes/bookings.js and MyBookings.jsx | Student page works and the lecturer list works in the API but has no page (D-03) | TC-09 and TC-25 | Fail | Partially Met
NFR-01 | A first-time student completes a booking in under 2 minutes | Non-Functional | Must | BookSlot.jsx three step flow | Scripted journey took 1.8 seconds. The timed test with students is planned for Week 5 | TC-10 | Not Tested | Partially Met
NFR-02 | The main pages load within 3 seconds in the team test set up | Non-Functional | Must | Vite production build | Slowest page load was 452 ms and slowest API call 19 ms | TC-11 and TC-23 and TC-24 | Pass | Met
NFR-03 | Every page works on a phone at 375 pixels wide and on a laptop at 1366 pixels wide | Non-Functional | Must | CSS container queries and responsive header | No sideways scrolling on the pages that exist. The lecturer page is not built | TC-12 | Pass | Partially Met
NFR-04 | Passwords are stored as bcrypt hashes and never as plain text | Non-Functional | Must | routes/auth.js and the seed script | All 7 stored passwords are bcrypt hashes. Repeated wrong passwords are not limited (D-06) | TC-13 | Pass | Met
NFR-05 | Each user can only see their own bookings or the bookings for their own slots | Non-Functional | Must | user_id checks in every query | Other users records were refused in every test | TC-14 and TC-09 | Pass | Met
NFR-06 | Only the data needed for logging in and booking is stored with made-up data during development | Non-Functional | Must | database/schema.sql and seed.sql | Five tables and no sensitive columns and all users on the test domain | TC-15 | Pass | Met
NFR-07 | Errors explain what to fix and the form keeps what the user already typed | Non-Functional | Should | middleware/validate.js and the page alerts | Plain messages and typed text kept. Two small issues logged (D-05 and D-08) | TC-16 and TC-16b and TC-28 | Fail | Partially Met